## Report Job Card List
Store Name | Job Number | Customer | Customer Code | Account Manager | Contact | Email | Mobile | Job Type | Description | Reference Number | Location | Start Date | Days Overall | Days In Status | Job Status | Status Date | Job Card Previous | Quote Number | Quote Amount | Linked Quotes | Invoice Number | Invoice Amount | Purchase Order Number | Customer Assets | Customer Asset Codes | Serial No | Materials | Assigned To | Fault Codes | Fault Causes | Fault Reasons | Custom Field 1 | Custom Field 2 | Custom Field 3 | Custom Field 4 | Custom Filter 1 | Custom Filter 2 | Custom Date 1 | Custom Date 2 | Custom Number 1 | Custom Number 2 | Closed | Status Flow | Queries | Is Active | Created Date | Created By | Modified By | Modified Date
Republic Energy & Metering (Pty) Ltd | JC10061 | BKB | CS10048 |  | Pauline Gerber | pauline.gerber@bkb.co.za |  | FF_Fault Fix Water (Lora/Visio) | Meter #1181702 has stopped comms. |  | BKB, BKB Building, 61 Grahamstown Rd, North End (Deon) | 2025-11-03 09:30:00 | 200 | 60 | FF10A_PT_Awaiting install by client's techie | 2026-03-23 08:59:48 |  |  |  | QU3404, QU3454 |  |  |  | Existing-150 mm Water Meter [1181702], FlowIQ® 4200 Q3 250 m³/h, DN150 x 300mm, PN16, Cold. linkIQ/Wireless M-Bus [54257692] | Existing-150 mm Water Meter, 02E-65-GCAR-8ZA | 1181702, 54257692 | FlowIQ® 4200 Q3 250 m³/h, DN150 x 300mm, PN16, Cold. linkIQ/Wireless M-Bus | Donovan Willemse |  |  |  | Sprinklers | [5 empty] | 2025-11-01 00:00:00 | 2025-11-03 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie |  | TRUE | 2025-11-03 09:29:59 | jamie@republicmetering.co.za | info@republicmetering.co.za | 2026-03-23 08:59:48
Republic Energy & Metering (Pty) Ltd | JC10062 | BKB | CS10048 |  | Pauline Gerber | pauline.gerber@bkb.co.za |  | FF_Fault Fix Water (Lora/Visio) | Meter #C-WRA0702 - ladies Cloakroom is showing no consumption. |  | BKB, BKB Building, 61 Grahamstown Rd, North End (Deon) | 2025-11-03 14:55:49 | 199 | 79 | FF10A_PT_Awaiting install by client's techie | 2026-03-03 15:26:54 |  |  |  | QU3171, QU3431 |  |  |  | Existing-20mm Water Meter [C-WRA0702], Existing-25mm Water Meter [C-BJK0742], Existing-150 mm Water Meter [1181702] | Existing-20mm Water Meter, Existing-25mm Water Meter, Existing-150 mm Water Meter | C-WRA0702, C-BJK0742, 1181702 | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 | Donovan Willemse |  |  |  | Ladies cloakroom and Retail Store | [5 empty] | 2025-11-03 00:00:00 | 2025-11-03 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF03.1_PT_Awaiting Client Feedback > FF04.1_FT_Quote population > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie |  | TRUE | 2025-11-03 14:55:49 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-03-18 06:16:50
Republic Energy & Metering (Pty) Ltd | JC10170 | Value Logistics (Pty) Ltd | CS10289 |  | Eugene Blanche | eugeneb@wonderlandprop.co.za |  | FF_Fault Fix Kamstrup Server Meter (Elec/Wat) | The meter has stopped communicating with us, checked the sim and it is also Offline |  | Nelspruit Value Logistics 32 Wilken St Rocky Drift Mbombela | 2026-01-06 14:27:09 | 136 | 3 | FF10B_PT_Schedule REM Tech installation/commission | 2026-05-19 09:27:03 | [7 empty] | Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [35726986] | 685-11-355-D24-0111-120 | 35726986 |  | Donovan Willemse, Lindy Maritz |  |  |  | Muni check | [5 empty] | 2025-12-24 00:00:00 | 2026-01-30 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback > FF10B_PT_Schedule REM Tech installation/commission |  | TRUE | 2026-01-06 14:27:09 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-19 09:27:03
REM - Work in Progress Warehouse | JC10204 | Summerpride Foods (Pty) Ltd | CS10255 |  | David Mandell | dave@summerpride.co.za |  | IN_Electrical Install (Client subbie) | Site Retrofit SPF is doing a retrofit and installing new Kamstrup meters to go on a DC. We are commissioning the meters. Old JC 589961 passed on to close. |  | Summerpride 2 Burgersdorp Road Gately Extension East London | 2026-01-14 10:35:31 | 128 | 0 | IN13.1_PT_Install complete capture info | 2026-05-22 09:31:33 |  |  |  | QU3192 | [7 empty] | Donovan Willemse, Justin Bezuidenhout | [13 empty] | FALSE | SI01_PT_Job Loaded > SI03.1_PT_Inspection Capture Info > IN11.1_PT_Awaiting install by client > IN11.2_PT_Schedule REM Tech installation/commission > IN13.1_PT_Install complete capture info |  | TRUE | 2026-01-14 10:35:31 | donovan@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-22 09:31:33
REM - Work in Progress Warehouse | JC10214 | BKB | CS10048 |  | Pauline Gerber | pauline.gerber@bkb.co.za |  | FF_Fault Fix Water (Lora/Visio) | Lora is recording zero consumption now, it must be faulty. Will have to quote to replace |  | BKB BKB Building 61 Grahamstown Rd North End (Deon) | 2026-01-15 15:41:57 | 126 | 123 | FF10A_PT_Awaiting install by client's techie | 2026-01-19 10:19:14 | [7 empty] | Existing-Unknown Water Meter [C-BJA1104], Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [76609168] | Existing-Unknown Water Meter, 021-40-C04-894 | C-BJA1104, 76609168 |  | Donovan Willemse |  |  |  | Gun Shop | [5 empty] | 2025-11-03 00:00:00 | 2025-11-03 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF10A_PT_Awaiting install by client's techie |  | TRUE | 2026-01-15 15:41:58 | donovan@republicmetering.co.za | donovan@republicmetering.co.za | 2026-03-19 12:48:10
REM - Work in Progress Warehouse | JC10223 | Richard and Roys Properties (Pty) Ltd | CS10740 |  | Shaun Xiao | pengfeizhiyi@hotmail.com | 0729701128 | IN_Electrical Install (REM Subbie) | Good afternoon Donovan, We have a total of 3 new retail stores to be metered, please see the following information as requested: Shop 5A - 420 Corner (This is where the two ATM's has been renovated into one shop) We would like to use the meter labelled as Nedbank (Ref: 1214131129245) for the new shop, This new shop is located in the space of Nedbank and ABSA combined. Please remove the ABSA meter (Ref: 34619130) completely as that meter will no longer be in use. Shop 10 - Salon Shop Shop 11A - Shah cell phone and accessories |  | Stanford Square Shopping Centre 45 Cottrell Street Kortsen Port Elizabeth | 2026-01-19 10:35:49 | 123 | 70 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-03-13 12:44:03 |  |  |  | QU3447 |  |  |  | AS230 Single Phase Meter [13112924], Kamstrup Omnipower V2 Single Phase Direct Connect 100 Amp Symmetrical Terminals No Battery [34619130] | EL-AS230, 686-12-111-N24-3101-120 | 13112924, 34619130 |  | Donovan Willemse, Jamie-Lee Ocks, Sean Knoetze, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI01_PT_Job Loaded > SI03.1_PT_Inspection Capture Info > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-01-19 10:35:50 | donovan@republicmetering.co.za | zoe@republicmetering.co.za | 2026-03-13 12:44:03
REM - Work in Progress Warehouse | JC10287 | Inofort Proprietary Limited [Coventry Works] | CS10127 |  | Chane Du Plessis | cduplessis@inospace.com |  | IN_Electrical Install (Client subbie) | Charné requested a quote for 2x Kamstrup meters. They are in the process of splitting Units 9 & 10. Meters to be installed inside each unit. |  | Coventry Works 675 Old Pretoria Rd, Halfway House, Midrand | 2026-02-03 09:25:47 | 108 | 106 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-02-05 08:31:46 |  |  |  | QU3327 | [7 empty] | Donovan Willemse, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-02-03 09:25:47 | donovan@republicmetering.co.za | donovan@republicmetering.co.za | 2026-04-24 12:58:51
REM - Work in Progress Warehouse | JC10299 | Thermelec | CS10275 |  | Mike Windsor | mike@thermelec.co.za | 0827840191 | IN_Electrical Install (Client subbie) | Mike Windsor requested a quote on meters and modems. Meters will be installed by them. We will commission once all the meters are installed. Billing entity will be Khan Property Group and the quote is to go to Thermelec. Please see completed BOQ form. |  | Site Manager 13 Sidon Rd North End Gqeberha | 2026-02-06 11:42:00 | 105 | 105 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-02-06 14:18:09 |  |  |  | QU3334, QU3350 | [7 empty] | Donovan Willemse, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-02-06 11:42:00 | donovan@republicmetering.co.za | zoe@republicmetering.co.za | 2026-02-06 14:18:10
REM - Work in Progress Warehouse | JC10313 | Value Logistics (Pty) Ltd | CS10289 |  | Eugene Blanche | eugeneb@wonderlandprop.co.za |  | IN_Electrical Install (Client subbie) | Hi Zoë I trust you are well. We require a cost quote for a demand meter at Value Express, 87 Maple Rd, Pomona. The quote is for a meter only plus modem. Please set up the meter for 500/5 CT’s . Please include forwarding cost. We will install and then liaise with Herloux on the day to ensure the meter is set up correctly. I will send through the meter name details for adding to our meter list. |  | Value Express 87 Maple Rd Pomona AH, Kempton Park, 1619 | 2026-02-10 08:32:15 | 101 | 52 | IN11.1_PT_Awaiting install by client | 2026-03-31 10:07:57 |  |  |  | QU3342 |  |  |  | Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [36823745], Riecktron M2M Kamstrup Plug In Modem (incl antenna) [MSK93970] | 685-11-355-D24-0111-120, M2M-MSK-A1 | 36823745, MSK93970 | Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp, Riecktron M2M Kamstrup Plug In Modem (incl antenna), Antennas | Donovan Willemse, Kyle de Agrella | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval > IN10_LT_ Job Approved Send Stock > IN11.1_PT_Awaiting install by client |  | TRUE | 2026-02-10 08:32:15 | kyle@republicmetering.co.za | kyle@republicmetering.co.za | 2026-05-07 08:11:05
REM - Work in Progress Warehouse | JC10322 | Prosperito Residential Fund (Pty) Ltd t/a The Grand Res | CS10218 |  | Melinda Botha | admin@thegrandres.co.za |  | IN_Electrical Install (REM Subbie) | Quotation required for 5x Single phase meters with 5x internal modems. |  | Grand Res 31 High St Makhanda | 2026-02-12 05:11:35 | 99 | 99 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-02-12 12:46:34 |  |  |  | QU3349 | [7 empty] | Donovan Willemse, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-02-12 05:11:36 | donovan@republicmetering.co.za | zoe@republicmetering.co.za | 2026-02-12 12:46:34
REM - Work in Progress Warehouse | JC10324 | BKB | CS10048 |  | Pauline Gerber | pauline.gerber@bkb.co.za |  | FF_Fault Fix Water (Lora/Visio) | The meter for the Retail store has stopped calling in. This is just to open a new JC on Servcraft, centricity ref 593512. Visio nr #00C86A07 |  | BKB, BKB Building, 61 Grahamstown Rd, North End (Deon) | 2026-02-12 16:18:55 | 98 | 79 | FF10A_PT_Awaiting install by client's techie | 2026-03-03 15:27:43 | [7 empty] | Existing-25mm Water Meter [C-BJK0742] | Existing-25mm Water Meter | C-BJK0742 | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 | Donovan Willemse |  |  |  | BKB Retail Store | [5 empty] | 2025-11-03 00:00:00 | 2026-01-05 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie |  | TRUE | 2026-02-12 16:18:56 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-03-10 11:16:27
REM - Work in Progress Warehouse | JC10331 | West Street Management (Pty) Ltd | CS10298 |  | Sharol Street Management (Pty) Ltd | weststreet.collections@gmail.com | 0718395901 | FF_Fault Fix Water (Lora/Visio) | Customer notified us our readings are out. The lora has recorded no consumption |  | Webbing Products 54 Paterson Road North End Gqebhera | 2026-02-13 12:50:58 | 98 | 94 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-02-17 14:15:56 |  |  |  | QU3357 |  |  |  | Existing-80mm Water Meter [341222], Existing-80mm Water Meter [11W715698], Existing-Unknown Water Meter [181162216] | Existing-80mm Water Meter, Existing-80mm Water Meter, Existing-Unknown Water Meter | 341222, 11W715698, 181162216 |  | Donovan Willemse, Zoë Wille |  |  |  | Main 1, main 2, unit 2 | [5 empty] | 2026-02-13 00:00:00 | 2026-05-13 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-02-13 12:50:58 | jamie@republicmetering.co.za | joanne@republicmetering.co.za | 2026-04-29 11:38:21
REM - Work in Progress Warehouse | JC10332 | Vestspruit Suites (Pty) Ltd | CS10294 |  | Deon Bekker | dbecker@trueprop.co.za |  | IN_Electrical Install (REM Subbie) | Please arrange for a quote to install a muni check meter. 9 Galaxy Ave, Frankenwald, Sandton, 2090 Fresenius Medical Care Deon Becker Facilities Manager Email: DBecker@trueprop.co.za Cel: +27 (0) 73 860 1128 Tel: +27 (0) 11 486 4970 Web: www.trueprop.co.za |  | Fresenius Medical Care 9 Galaxy Ave Frankenwald Sandton | 2026-02-13 13:40:22 | 98 | 57 | SI03.1_PT_Inspection Capture Info | 2026-03-26 13:02:36 | [11 empty] | Donovan Willemse, Joanne Kumm | [13 empty] | FALSE | SI01_PT_Job Loaded > SI03.1_PT_Inspection Capture Info |  | TRUE | 2026-02-13 13:40:22 | joanne@republicmetering.co.za | joanne@republicmetering.co.za | 2026-03-26 13:02:36
REM - Work in Progress Warehouse | JC10336 | Thermelec | CS10275 |  | Mike Windsor | mike@thermelec.co.za | 0827840191 | IN_Water Install (Client is installing) | Mike reached out to AE for a quote: (Supply and commission only) Qtys provided as per AE: 60x gateways 50x Dn20s 1x DN50 10x Pit antennas 60x hrs commissioning fee (Full list price) No Site Inspection |  | Unknown P O Box 5141 Walmer | 2026-02-16 09:29:46 | 95 | 95 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-02-16 12:39:35 |  |  |  | QU3353 | [7 empty] | Donovan Willemse, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-02-16 09:29:46 | zoe@republicmetering.co.za | donovan@republicmetering.co.za | 2026-03-09 11:47:46
REM - Work in Progress Warehouse | JC10343 | Milprops 365 (Pty) Ltd | CS10179 |  | Melissa Russell | maintenance@mp365.co.za |  | FF_Fault Fix Water (Lora/Visio) | Two meters for Units A07 & C04 has lost comms since the beginning of the month. we need to resolve comms or quote on replacing. Please note this is prepaid so we would prefer for it to be resolved. |  | Maitland Industrial Park, Voortrekker Road, Maitland, Cape Town (Alwyn) | 2026-02-17 11:57:41 | 94 | 94 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-02-17 12:11:12 | [7 empty] | Box Complete-20MM Plastic SA1508 SABS V (BCP20M20) [210401848], Box Complete-20MM Plastic SA1508 SABS V (BCP20M20) [210401885] | PR-DWM-PVC-20/20mm, PR-DWM-PVC-20/20mm | 210401848, 210401885 |  | Donovan Willemse, Kyle de Agrella |  |  |  | Unit A07 & C04 | [5 empty] | 2026-02-02 00:00:00 | 2026-02-27 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-02-17 11:57:42 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-04-22 10:45:41
REM - Work in Progress Warehouse | JC10433 | Brunfelsia Investment Holdings (Pty) Ltd C/O Trueprop Property Services (Pty) Ltd | CS10684 |  | Shane Robinson | SRobinson@trueprop.co.za |  | IN_Electrical Install (REM Subbie) | Hi Zoe, Can you please assist with a quote for the subject property? Electrical and Water meters. I would propose that you attend to a site inspection and draw up a single line diagram for the property. Kind Regards, Shane Robinson |  | The Local Kyalami Park Kyalami Blvd Johannesburg | 2026-03-04 09:22:35 | 79 | 17 | SI03.1_PT_Inspection Capture Info | 2026-05-05 10:53:19 |  |  |  | QU3437 | [7 empty] | Donovan Willemse, James Nicholls, Lindy Maritz | [13 empty] | FALSE | SI01_PT_Job Loaded > SI02_PT_Inspection Scheduled > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval > IN11.2_PT_Schedule REM Tech installation/commission > SI02_PT_Inspection Scheduled > IN13.1_PT_Install complete capture info > SI02_PT_Inspection Scheduled > SI03.1_PT_Inspection Capture Info |  | TRUE | 2026-03-04 09:22:35 | donovan@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-05 10:53:20
REM - Work in Progress Warehouse | JC10434 | Brunfelsia Investment Holdings (Pty) Ltd C/O Trueprop Property Services (Pty) Ltd | CS10684 |  | Shane Robinson | SRobinson@trueprop.co.za |  | IN_Water Install (Client is installing) | Hi Zoe, Can you please assist with a quote for the subject property? Electrical and Water meters. I would propose that you attend to a site inspection and draw up a single line diagram for the property. Kind Regards, Shane Robinson |  | The Local Kyalami Park Kyalami Blvd Johannesburg | 2026-03-04 11:51:29 | 79 | 8 | SI03.1_PT_Inspection Capture Info | 2026-05-14 12:22:11 | [11 empty] | Donovan Willemse, James Nicholls, Lindy Maritz | [13 empty] | FALSE | SI01_PT_Job Loaded > SI03.1_PT_Inspection Capture Info > SI02_PT_Inspection Scheduled > SI03.1_PT_Inspection Capture Info > SI03.2_QT_Quotation Sign Off > SI03.1_PT_Inspection Capture Info |  | TRUE | 2026-03-04 11:51:29 | donovan@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-14 12:22:12
Republic Energy & Metering (Pty) Ltd | JC10490 | West Street Management (Pty) Ltd | CS10298 |  | Lillian Unknown | toddcharterhouse@gmail.com | 0652405134 | FF_Fault Fix Water (Lora/Visio) | Meter is still connected to a visio ( 02038797) we need to replace with a KMP water meter. |  | Pearson Street Gqeberha Central Gqeberha 6001 | 2026-03-12 08:34:35 | 71 | 30 | FF10A_PT_Awaiting install by client's techie | 2026-04-22 08:26:04 |  |  |  | QU3453 |  |  |  | Existing-15mm Water Meter [212069480], Existing-15mm Water Meter [242016033] | Existing-15mm Water Meter, Existing-15mm Water Meter | 212069480, 242016033 | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 | Donovan Willemse, Zoë Wille |  |  |  | Meter 2 & 3 | [5 empty] | 2026-03-04 00:00:00 | 2026-06-04 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie |  | TRUE | 2026-03-12 08:34:36 | jamie@republicmetering.co.za | info@republicmetering.co.za | 2026-04-22 08:26:04
Republic Energy & Metering (Pty) Ltd | JC10494 | Captivate Investment Trust | CS10062 |  | Lindsay Vroom | lindsayvroom@itsnet.co.za |  | FF_Fault Fix Kamstrup Server Meter (Elec/Wat) | Meter is connected to a KoCos modem and has not called in for a few days. |  | Vroom Industrial Strowan Road Industrial Area Grahamstown | 2026-03-13 09:10:18 | 70 | 31 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-04-21 12:21:24 |  |  |  | QU3557 |  |  |  | AS3000 Three Phase SMART Meter (AS3000) [6819237], A1140 Three Phase 4W 5A 230V 0.5 TOU RS232 ESK Complex Mid-Range Meters [78102692] | EL-AS3000, LM3MAABBNHESRBFESK | 6819237, 78102692 |  | Donovan Willemse, Justin Bezuidenhout, Zoë Wille |  |  |  | Unit 4 - Bruce Little + Muni check | [5 empty] | 2026-03-11 00:00:00 | 2026-03-31 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-03-13 09:10:20 | jamie@republicmetering.co.za | zoe@republicmetering.co.za | 2026-04-21 12:21:24
REM - Work in Progress Warehouse | JC10499 | Seven Seasons 214 (Pty) Ltd | CS10234 |  | Sharon Fynn | sharonfynn@imaginet.co.za | 2712345678 | FF_Fault Fix Water (Lora/Visio) | Meter is still connected to a visio (02016D2A) we need to quote on replacing with a KMP - but it is Gertz so not sure how we are going to approach this. |  | Site Manager Unknown | 2026-03-13 12:43:38 | 70 | 0 | FF12.1_PT_Install complete capture info | 2026-05-22 08:30:33 |  |  |  | QU3451 |  |  |  | Existing-20mm Water Meter [222025119], Visios [02016D2A], Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [76088556], Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 [54043164] | Existing-20mm Water Meter, VIS-VISIO, 021-40-C04-894, 02K-51-AC6G-8ZA | 222025119, 02016D2A, 76088556, 54043164 | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 | Donovan Willemse, Justin Bezuidenhout, Lindy Maritz |  |  |  | Hillcrest - SARS Main Office | [5 empty] | 2026-02-17 00:00:00 | 2026-05-14 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie > FF12.1_PT_Install complete capture info > FF10A_PT_Awaiting install by client's techie > FF12.2_QT_Install Sign Off > FF12.1_PT_Install complete capture info |  | TRUE | 2026-03-13 12:43:38 | jamie@republicmetering.co.za | lindy@republicmetering.co.za | 2026-05-22 08:30:34
REM - Work in Progress Warehouse | JC10501 | Inospace 3 Proprietary Limited [Eastleigh Exchange] | CS10141 |  | Leander Grobbelaar | lgrobbelaar@inospace.com |  | IN_Electrical Install (Client subbie) | Good day We need 2 new meters to be supplied to eastleigh exchange as we splitted power for unit 4b and 4c. Regards Leander Grobbelaar |  | Eastleigh Exchange 37 Main Road, Eastleigh, Edenvale, 1609 (Leander) | 2026-03-13 15:46:27 | 69 | 3 | IN16_PT_Reschedule for a fix (issues found on setup) | 2026-05-19 11:11:10 |  |  |  | QU3456, QU3623 |  |  |  | Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [36793074], Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [36793071], Riecktron M2M Kamstrup Plug In Modem (incl antenna) [MSK85706], Riecktron M2M Kamstrup Plug In Modem (incl antenna) [MSK93980] | 685-11-355-D24-0111-120, 685-11-355-D24-0111-120, M2M-MSK-A1, M2M-MSK-A1 | 36793074, 36793071, MSK85706, MSK93980 | Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp, Riecktron M2M Kamstrup Plug In Modem (incl antenna), Antennas, Ring CT 30/40mm ID 200/5A CLS 0,5 | Donovan Willemse | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval > IN10_LT_ Job Approved Send Stock > IN11.1_PT_Awaiting install by client > IN16_PT_Reschedule for a fix (issues found on setup) > SI03.2_QT_Quotation Sign Off > SI04_FT_Quote Population > IN16_PT_Reschedule for a fix (issues found on setup) |  | TRUE | 2026-03-13 15:46:28 | donovan@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-19 11:11:14
REM - Work in Progress Warehouse | JC10556 | Superspar Spargs Butterworh | CS10822 |  | Wayne Preston | wayne@spargs.co.za | 0836294100 | IN_Electrical Install (REM Subbie) | U CAN SOLAR reached out requesting a check meter. They would like to get profile to aid in designing the clients solar system. |  | Sauer St, Gcuwa, 4960 | 2026-03-24 11:11:39 | 59 | 4 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-05-18 09:53:40 |  |  |  | QU3625 | [7 empty] | Donovan Willemse, Justin Bezuidenhout, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI02_PT_Inspection Scheduled > SI03.2_QT_Quotation Sign Off > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-03-24 11:11:40 | donovan@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-18 09:53:40
REM - Work in Progress Warehouse | JC10557 | Superspar Spargs Butterworh | CS10822 |  | Wayne Preston | wayne@spargs.co.za | 0836294100 | IN_Water Install (Client is installing) | Client has requested that we quote him on water as well as elec (JC10556). Waiting for additional info. |  | Sauer St, Gcuwa, 4960 | 2026-03-24 11:38:01 | 59 | 4 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-05-18 09:54:17 | [11 empty] | Donovan Willemse, Justin Bezuidenhout, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI02_PT_Inspection Scheduled > SI03.2_QT_Quotation Sign Off > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-03-24 11:38:01 | donovan@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-18 09:54:17
REM - Work in Progress Warehouse | JC10559 | Adomix (Pty) Ltd | CS10023 |  | Lee-Ann Stabsfield | lee-ann@wgproperties.co.za | 0606317571 | FF_Fault Fix Water Kamstrup with Gateway | These meters have not called in for a few days. Please can we resolve comms |  | Wellington Square Wellington Street Bodorp George | 2026-03-25 08:38:05 | 58 | 0 | FF11_PT_Could not complete reschedule | 2026-05-22 06:11:42 | [7 empty] | Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [77698169], Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [77698135], Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [77698174], Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [76685566], Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [77698171], Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [77698136], Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [77698137], Existing Comms Device [MSL38426] | 021-40-C04-894, 021-40-C04-894, 021-40-C04-894, 021-40-C04-894, 021-40-C04-894, 021-40-C04-894, 021-40-C04-894, Existing Comms Device | 77698169, 77698135, 77698174, 76685566, 77698171, 77698136, 77698137, MSL38426 |  | Donovan Willemse |  |  |  | Multiple | [5 empty] | 2026-03-22 00:00:00 | 2026-04-14 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback > FF10B_PT_Schedule REM Tech installation/commission > FF15.3_FT_Final invoice and check monthlies > FF11_PT_Could not complete reschedule |  | TRUE | 2026-03-25 08:38:07 | jamie@republicmetering.co.za | susan@republicmetering.co.za | 2026-05-22 06:11:43
REM - Work in Progress Warehouse | JC10597 | Richard and Roys Properties (Pty) Ltd | CS10740 |  | Chantené Kiewiets | stanfordsquare974@gmail.com | 0729701128 | IN_Water Install (Client is installing) | Hi Jamie-Lee, Would you perhaps know who removed it (i.e was it Republic metering, Western gruppe or the tenant themselves), so that Icould try and investigate where the meter currently is. Furthermore, if the meter is found I would like to request that it be reinstalled please. If in the case that the meter is not found I would please like to request that it be replaced as soon as possible and added to the monthly monitored tenant accounts please. I hope you are able to understand my request. Please reach out if you have any questions or concerns. Thank you so much in advance. Kind Regards, Chantené Kiviets Stanford Square Admin Richard and Roy's Properties Email: stanfordsquare974@gmail.com Call: 072 970 1128 |  | Stanford Square Shopping Centre 45 Cottrell Street Kortsen Port Elizabeth | 2026-03-26 15:54:09 | 56 | 15 | IN15_BT_Billing Scada Setup | 2026-05-07 12:45:01 |  |  |  | QU3496 |  |  |  | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 [54043157], Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [76685529] | 02K-51-AC6G-8ZA, 021-40-C04-894 | 54043157, 76685529 | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 | Donovan Willemse, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval > IN10_LT_ Job Approved Send Stock > IN11.1_PT_Awaiting install by client > IN13.2_QT_Install Sign Off > IN14_LT_Update Stock Used > IN15_BT_Billing Scada Setup |  | TRUE | 2026-03-26 15:54:09 | donovan@republicmetering.co.za | jamie@republicmetering.co.za | 2026-05-21 12:37:39
REM - Work in Progress Warehouse | JC10603 | Bishops Glen Farm | CS10824 |  | Dylan Berndts | dyllanberndt@yahoo.com | 0828902446 | IN_Electrical Install (REM Subbie) | Morning Donny. Hope you are well bud. We went to view another site last week. It is a farm up near Bloem, Free State. They also require energy meters - they have 6 points from Eskom around the farm. Need a Quote on installing meters there; Justin will be accommodated on the Farm, so that’s no issue. |  | Bishops Glen Farm X8XV+M5C Bloemfontein | 2026-03-30 09:09:56 | 53 | 51 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-03-31 16:12:05 |  |  |  | QU3495, QU3508 | [7 empty] | Donovan Willemse, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-03-30 09:09:56 | donovan@republicmetering.co.za | zoe@republicmetering.co.za | 2026-03-31 16:12:05
REM - Work in Progress Warehouse | JC10610 | BKB | CS10048 |  | Deon Erasmus | deon.erasmus@bkb.co.za | 0828607176 | FF_Fault Fix Water (Lora/Visio) | Some water meters at BKB are recording zero consumption, I have been drawing attention to this when sending the billing and asking for confirmation however we receive no response. I am almost certain that there should be consumption on these meters. C-WRA0703, C-WRA0702, C-WRA0698 and 3143359. |  | BKB BKB Building 61 Grahamstown Rd North End (Deon) | 2026-03-30 15:26:12 | 52 | 39 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-04-13 09:20:02 |  |  |  | QU3524 |  |  |  | Existing-20mm Water Meter [C-WRA0703], Existing-20mm Water Meter [C-WRA0698], Existing-100MM Water Meter [3143359] | Existing-20mm Water Meter, Existing-20mm Water Meter, Existing-100MM Water Meter | C-WRA0703, C-WRA0698, 3143359 |  | Donovan Willemse, Zoë Wille |  |  |  | Warehouse, Modiano, Ladies Cloakroom, Drying Room Heatpump | [5 empty] | 2026-03-30 00:00:00 | 2026-06-30 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-03-30 15:26:13 | chelsea@republicmetering.co.za | zoe@republicmetering.co.za | 2026-04-13 09:20:02
REM - Work in Progress Warehouse | JC10613 | GM Industrial Park Body Corporate (SLA) | CS10109 |  | Neill Hodgskin | maintenance@bmiza.com | 0719007429 | FF_Fault Fix Kamstrup Server Meter (Elec/Wat) | This meter calls in when the date is set back manually, then a day later it is back on the problem meter list. Can we somehow resolve this for good? Refer to previous comment on JC completed by JK |  | GM Industrial Park Kempston Road Gqebhera 6001 (Neill) | 2026-03-31 08:43:41 | 52 | 0 | FF04.1_FT_Quote population | 2026-05-22 14:20:23 | [7 empty] | Kamstrup DN15 (20mm) FlowIQ2200 Composite Threaded 110mm cold water 1.5kl/h R250 WM-Bus/LinkIQ [12992719] | 02K-51-AC1B-817 | 12992719 |  | Donovan Willemse, Zoë Wille |  |  |  | Coling Barris Agencies | [5 empty] | 2026-03-25 00:00:00 | 2026-03-31 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF02.2_PT_Further Investigations > FF03.3_QT_Quotation Sign Off > FF04.1_FT_Quote population |  | TRUE | 2026-03-31 08:43:42 | jamie@republicmetering.co.za | lindy@republicmetering.co.za | 2026-05-22 14:20:23
REM - Work in Progress Warehouse | JC10617 | Waterlea Dairy PTY LTD | CS10297 |  | Mark Holliday | mark@xantium.org |  | FF_Fault Fix Elec meter with modem | the full load meter has not been calling in. |  | Unknown Waterlea Hofmeyr | 2026-03-31 08:57:36 | 52 | 31 | FF03.1_PT_Awaiting Client Feedback | 2026-04-20 15:27:14 | [7 empty] | Riecktron M2M Kamstrup Plug In Modem (incl antenna) [MSK66222], Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [35775682] | M2M-MSK-A1, 685-11-355-D24-0111-120 | MSK66222, 35775682 |  | Donovan Willemse |  |  |  | Full load meter | [5 empty] | 2026-03-27 00:00:00 | 2026-04-01 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback |  | TRUE | 2026-03-31 08:57:37 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-04-20 15:27:14
REM - Work in Progress Warehouse | JC10620 | Raumix Aggregates | CS10813 |  | Neil Joubert | rossway@raumix.co.za | 0788035132 | IN_Electrical Install (REM Subbie) | Client requested a SI to determine the requirements to meter the whole quarry. |  | Rossway Quarry Olievenhoutbosch Olievenhoutbosch Centurion 0187 | 2026-03-31 11:35:37 | 52 | 17 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-05-05 10:46:34 |  |  |  | QU3596 | [7 empty] | Donovan Willemse, James Nicholls, Lindy Maritz, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI02_PT_Inspection Scheduled > SI03.1_PT_Inspection Capture Info > SI03.2_QT_Quotation Sign Off > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-03-31 11:35:38 | donovan@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-05 10:46:34
REM - Work in Progress Warehouse | JC10622 | Raumix Aggregates | CS10813 |  | Obakeng Motlhamme (Donkerhoek) | obakeng.m@raumix.co.za | 27769914460 | IN_Electrical Install (REM Subbie) | U CAN SOLAR site Client requested a SI to determine the requirements to meter the whole quarry. |  | Raumix Donkerhoek Plot 115 R104 Old Bronkhorstspruit Rd | 2026-03-31 11:48:28 | 52 | 17 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-05-05 11:10:55 |  |  |  | QU3577 | [7 empty] | Donovan Willemse, James Nicholls, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-03-31 11:48:29 | donovan@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-05 11:10:55
REM - Work in Progress Warehouse | JC10623 | Raumix Aggregates | CS10813 |  | Kobus Le Roux | kobus.l@raumix.co.za | 0714627717 | IN_Electrical Install (REM Subbie) | Client requested a SI to determine the requirements to meter the whole quarry. |  | Raumix Aggregates Rosslyn Quarry Soshanguve, 0164 | 2026-03-31 11:51:25 | 52 | 17 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-05-05 11:33:23 |  |  |  | QU3595 | [7 empty] | Donovan Willemse, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI02_PT_Inspection Scheduled > SI03.1_PT_Inspection Capture Info > SI03.2_QT_Quotation Sign Off > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-03-31 11:51:26 | donovan@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-05 11:33:23
REM - Work in Progress Warehouse | JC10634 | West Street Management (Pty) Ltd | CS10298 |  | Lillian Unknown | toddcharterhouse@gmail.com | 0652405134 | FF_Fault Fix Water (Lora/Visio) | The Newton Park main is not calling in. |  | Newton Park Cnr West St &, 3rd Ave Newton Park Gqeberha | 2026-04-02 11:11:53 | 50 | 30 | FF10A_PT_Awaiting install by client's techie | 2026-04-22 08:27:05 |  |  |  | QU3540 |  |  |  | Existing-80mm Water Meter [18741058], Existing-20mm Water Meter [222013408], Existing-Unknown Water Meter [181138546] | Existing-80mm Water Meter, Existing-20mm Water Meter, Existing-Unknown Water Meter | 18741058, 222013408, 181138546 |  | Donovan Willemse, Zoë Wille |  |  |  | Main | [5 empty] | 2026-03-28 00:00:00 | 2026-06-30 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie |  | TRUE | 2026-04-02 11:11:54 | jamie@republicmetering.co.za | info@republicmetering.co.za | 2026-04-22 08:27:05
REM - Work in Progress Warehouse | JC10655 | The Circle (Pty) Ltd | CS10267 |  | Lize Price | LPrice@trueprop.co.za | 0609611007 | FF_Fault Fix Water (Lora/Visio) | Meter is still connected to visio ( 02033DAE ) but has not recorded any consumption. |  | Kings Mall Main Road East London 5201 | 2026-04-08 14:20:28 | 44 | 35 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-04-17 13:14:06 |  |  |  | QU3536 |  |  |  | Visios [02033DAE], Existing-20mm Water Meter [C-SAG8537] | VIS-VISIO, Existing-20mm Water Meter | 02033DAE, C-SAG8537 |  | Donovan Willemse, Zoë Wille |  |  |  | Shop 11 - Miladys | [5 empty] | 2026-03-10 00:00:00 | 2026-06-05 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-08 14:20:29 | jamie@republicmetering.co.za | zoe@republicmetering.co.za | 2026-04-17 13:14:06
REM - Work in Progress Warehouse | JC10660 | Smartt Tech Solutions (Pty) Ltd | CS10670 |  | Dr Forward Muchaonyerwa | forward.mucha@skg.co.za | 0739006538 | FF_Fault Fix Kamstrup Server Meter (Elec/Wat) | Two meters at Wilsonia have stopped communicating with us. |  | PR176 Cut Rag Building (Wilsonia) 20 Bert Kipling Road Wilsonia East London | 2026-04-09 08:05:05 | 43 | 1 | FF09.2_LT_Job Approved Send Stock | 2026-05-21 10:07:53 | [7 empty] | Kamstrup DN80 FlowIQ3200 Stainless Steel Flanged 300mm cold water 40kl/h R250 WM-Bus/LinkIQ [54258004], Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [36401946] | 02L-60-DC6W-8ZA, 684-11-311-N24-5111-120 | 54258004, 36401946 |  | Donovan Willemse, Justin Bezuidenhout, Lizette Benn |  |  |  | Wilsonia Building - Muni Check & Staff Canteen | [5 empty] | 2026-04-04 00:00:00 | 2026-04-16 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF10B_PT_Schedule REM Tech installation/commission > FF09.2_LT_Job Approved Send Stock |  | TRUE | 2026-04-09 08:05:09 | jamie@republicmetering.co.za | susan@republicmetering.co.za | 2026-05-21 10:08:01
REM - Work in Progress Warehouse | JC10665 | InoFort (Pty) Ltd [Textile Exchange] | CS10126 |  | Liam Vickers | lvickers@inospace.com |  | FF_Fault Fix Water (Lora/Visio) | The meter is still connected to a visio ( 01FB2C8E) and we need to quote on replacing with a KMP water meter |  | Textile Exchange 19 Textiel Street Parow Industria Cape Town | 2026-04-10 09:55:46 | 42 | 35 | FF10A_PT_Awaiting install by client's techie | 2026-04-17 09:37:16 |  |  |  | QU3538 |  |  |  | Visios [01FB2C8E], Existing-20mm Water Meter [232057762], Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 [54043160] | VIS-VISIO, Existing-20mm Water Meter, 02K-51-AC6G-8ZA | 01FB2C8E, 232057762, 54043160 | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 | Donovan Willemse |  |  |  | Unit WB03A - New Rama Super Store | [5 empty] | 2026-04-07 00:00:00 | 2026-06-08 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie |  | TRUE | 2026-04-10 09:55:48 | jamie@republicmetering.co.za | susan@republicmetering.co.za | 2026-04-23 09:56:17
REM - Work in Progress Warehouse | JC10667 | Milprops 365 (Pty) Ltd | CS10179 |  | Melissa Russell | maintenance@mp365.co.za |  | FF_Fault Fix Water (Lora/Visio) | Previous JCs on centricity (JC570285, 565033, 588407) was not repopened. Meters has not called in. Still connected to a lora's |  | Nautica MR559 Langebaan 7357 | 2026-04-10 14:23:23 | 42 | 17 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-05-05 11:14:41 |  |  |  | QU3539 |  |  |  | Existing-20mm Water Meter [21000232], Existing-20mm Water Meter [21000241], Existing-20mm Water Meter [21000242] | Existing-20mm Water Meter, Existing-20mm Water Meter, Existing-20mm Water Meter | 21000232, 21000241, 21000242 |  | Donovan Willemse, Zoë Wille |  |  |  | Shop 08; Shop 17; Shop 22 | [5 empty] | 2026-03-25 00:00:00 | 2026-04-30 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-10 14:23:24 | jamie@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-05 11:14:41
REM - Work in Progress Warehouse | JC10668 | Seven Seasons 214 (Pty) Ltd | CS10234 |  | Duonette Horowitz | admin2@wgproperties.co.za |  | FF_Fault Fix Water Kamstrup with Gateway | The water meter has not called in, on the 14th of last month we added an estimation, and it has not called in since |  | Site Manager Unknown | 2026-04-10 14:30:34 | 42 | 22 | FF10B_PT_Schedule REM Tech installation/commission | 2026-04-30 11:14:26 | [7 empty] | Existing-Unknown Water Meter [68607000] | Existing-Unknown Water Meter | 68607000 |  | Donovan Willemse, Justin Bezuidenhout |  |  |  | Spar Main | [5 empty] | 2026-03-01 00:00:00 | 2026-04-14 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback > FF10B_PT_Schedule REM Tech installation/commission |  | TRUE | 2026-04-10 14:30:35 | jamie@republicmetering.co.za | jamie@republicmetering.co.za | 2026-05-15 11:59:29
REM - Work in Progress Warehouse | JC10670 | Trueprop Industrial One | CS10284 |  | Olivia Erasmus | oerasmus@trueprop.co.za |  | FF_Fault Fix Elec meter with modem | Multiple meters connected to modem (MSS51837) |  | Site Manager 3 Fuchs St Alrode Alberton | 2026-04-13 09:30:49 | 39 | 35 | FF03.1_PT_Awaiting Client Feedback | 2026-04-16 14:59:06 | [7 empty] | Kamstrup Omnipower V2 Single Phase Direct Connect 100 Amp Symmetrical Terminals No Battery [34321497], Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [35727109], Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [35727082], Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [35724468], Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [35724467] | 686-12-111-N24-3101-120, 685-11-355-D24-0111-120, 685-11-355-D24-0111-120, 684-11-311-N24-5111-120, 684-11-311-N24-5111-120 | 34321497, 35727109, 35727082, 35724468, 35724467 |  | Donovan Willemse, Jamie-Lee Ocks |  |  |  | Multiple - Unit 3 & 6 | [5 empty] | 2026-04-09 00:00:00 | 2026-05-05 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback |  | TRUE | 2026-04-13 09:30:50 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-04-16 14:59:06
REM - Work in Progress Warehouse | JC10673 | Raumix Aggregates | CS10813 |  | Stephen Grilli (Crushco Quarry) | Stephen.G@raumix.co.za | 27836360984 | IN_Electrical Install (REM Subbie) | Client requested a SI to determine the requirements to meter the whole quarry. |  | Raumix Crushco Quarry, 9th Road Bredell, Kempton Park, 1501 | 2026-04-13 13:39:04 | 39 | 22 | SI02_PT_Inspection Scheduled | 2026-04-30 10:25:21 | [11 empty] | Donovan Willemse, James Nicholls, Lindy Maritz | [13 empty] | FALSE | SI01_PT_Job Loaded > SI02_PT_Inspection Scheduled |  | TRUE | 2026-04-13 13:39:05 | donovan@republicmetering.co.za | donovan@republicmetering.co.za | 2026-04-30 10:25:21
REM - Work in Progress Warehouse | JC10677 | West Street Management (Pty) Ltd | CS10298 |  | Lillian Unknown | toddcharterhouse@gmail.com | 0652405134 | FF_Fault Fix Water (Lora/Visio) | The meter rolled over and the lora is also faulty and not recording the correct consumption. There was a leak and it did not pick it up |  | Todd Chambers Building 16 Todd St, North End, Gqeberha, 6001 | 2026-04-14 12:25:31 | 38 | 30 | FF10A_PT_Awaiting install by client's techie | 2026-04-22 08:27:55 |  |  |  | QU3548 |  |  |  | Existing-20mm Water Meter [19A026440] | Existing-20mm Water Meter | 19A026440 | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 | Donovan Willemse, Zoë Wille |  |  |  | Todd Chambers Building muni check | [5 empty] | 2026-04-14 00:00:00 | 2026-04-14 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie |  | TRUE | 2026-04-14 12:25:32 | jamie@republicmetering.co.za | info@republicmetering.co.za | 2026-04-22 08:27:55
REM - Work in Progress Warehouse | JC10682 | Donsure Properties (PTY) Ltd | CS10086 |  | Nandipha Hasi | NHasi@trueprop.co.za | 0829353214 | FF_Fault Fix Water (Lora/Visio) | Meter is still connected to a visio. We need to quote on replacing for a smart meter. |  | 6 - 8 Donald Rd Vincent East London 5241 | 2026-04-14 16:25:41 | 37 | 7 | FF15.1_PT_Reschedule for a fix (issues found on setup) | 2026-05-15 11:58:54 |  |  |  | QU3552 |  |  |  | Visios [00C887DA], Existing-15mm Water Meter [222035328], Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 [54043158] | VIS-VISIO, Existing-15mm Water Meter, 02K-51-AC6G-8ZA | 00C887DA, 222035328, 54043158 | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 | Donovan Willemse |  |  |  | Unit 1F7 - Regent Business School - Toilets | [5 empty] | 2026-04-10 00:00:00 | 2026-07-06 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie > FF12.2_QT_Install Sign Off > FF13_LT_Update Stock Used > FF14_BT_Billing Scada Setup > FF15.1_PT_Reschedule for a fix (issues found on setup) |  | TRUE | 2026-04-14 16:25:42 | jamie@republicmetering.co.za | chelsea@republicmetering.co.za | 2026-05-21 10:28:08
REM - Work in Progress Warehouse | JC10684 | Wynberg Works Body Corporate C/O De Lucia Properties (Pty) Ltd | CS10531 |  | Annecke de Clerk | anneckedc@delucia.co.za |  | IN_Electrical Install (Client subbie) | Replace Unit 15.1 Prepaid meter - Citiq #54746791372 Single Phase meter |  | Courtney Thompson 40 5th St Wynberg, Sandton 2090 | 2026-04-15 10:00:38 | 37 | 22 | IN11.1_PT_Awaiting install by client | 2026-04-30 09:36:36 |  |  |  | QU3551 | [7 empty] | Donovan Willemse | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI05_FT_Quote Review > SI07_FT_Quote Sent Awaiting Customer Approval > IN10_LT_ Job Approved Send Stock > IN11.2_PT_Schedule REM Tech installation/commission > IN11.1_PT_Awaiting install by client |  | TRUE | 2026-04-15 10:00:39 | lindy@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-08 10:24:05
REM - Work in Progress Warehouse | JC10685 | GONUBIE MOTORS CC | CS10834 |  | Mike J Smith | Mjsmith@bos.co.za | 0832271894 | IN_Electrical Install (REM Subbie) | U CAN SOLAR Site Mike from Gonubie Motor requested a quote for a muni check meter. |  | Gonubie Shell Garage 17 Main Rd Gonubie KuGompo | 2026-04-15 15:36:26 | 36 | 31 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-04-21 11:32:39 |  |  |  | QU3558, QU3559 | [7 empty] | Donovan Willemse, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-15 15:36:27 | lindy@republicmetering.co.za | lindy@republicmetering.co.za | 2026-04-28 08:49:44
REM - Work in Progress Warehouse | JC10686 | West Street Management (Pty) Ltd | CS10298 |  | Lillian Unknown | toddcharterhouse@gmail.com | 0652405134 | FF_Fault Fix Water (Lora/Visio) | Comp Air Workshop. Lillian does not want the replace this meter immediately but some time into the future. Sending a separate quote so they can have it in the meantime. |  | Webbing Products 54 Paterson Road North End Gqebhera | 2026-04-15 16:01:49 | 36 | 30 | FF10A_PT_Awaiting install by client's techie | 2026-04-22 08:29:51 |  |  |  | QU3550 |  |  |  | Existing-15mm Water Meter [191046620] | Existing-15mm Water Meter | 191046620 | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 | Donovan Willemse, Zoë Wille |  |  |  | Comp Air Workshop | [5 empty] | 2026-04-01 00:00:00 | 2026-04-01 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF04.1_FT_Quote population > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie |  | TRUE | 2026-04-15 16:01:51 | susan@republicmetering.co.za | info@republicmetering.co.za | 2026-04-22 08:29:51
REM - Work in Progress Warehouse | JC10687 | Lumibiz (PTY) Ltd | CS10169 |  | Abraham Marais | abraham@fvcec.co.za | 0836318822 | FF_Fault Fix Water (Lora/Visio) | Meter is still connected to a visio and it has stopped communicating with us. We need to quote on replacing the meter with a smart meter. |  | Abraham Marais Woestyn Close Montana Tuine Pretoria | 2026-04-16 08:08:52 | 36 | 17 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-05-05 11:44:55 |  |  |  | QU3574 |  |  |  | Visios [020148C4], Multi-jet Meter Brass, CL B with Reed Switch 50mm [201112879] | VIS-VISIO, PR-MJM-Brass-50mm | 020148C4, 201112879 |  | Donovan Willemse, Jamie-Lee Ocks, Zoë Wille |  |  |  | Meter 3 | [5 empty] | 2026-04-12 00:00:00 | 2026-07-20 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-16 08:08:54 | jamie@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-05 11:44:55
REM - Work in Progress Warehouse | JC10700 | PE Fishing Enterprises (Pty) Ltd | CS10201 |  | Abraham Marais | abraham@fvcec.co.za | 0836318822 | FF_Fault Fix Kamstrup Server Meter (Elec/Wat) | 24721480 has not called. I will estimate it now till the 17th of April. Billing due 19th. |  | Cornerstone 20 London Circle Brackenfell South Cape Town | 2026-04-20 10:35:27 | 32 | 15 | FF10B_PT_Schedule REM Tech installation/commission | 2026-05-07 10:11:16 | [7 empty] | Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [24721480] | 021-40-C04-894 | 24721480 |  | Donovan Willemse, Shane Bowers |  |  |  | Unit 37 | [5 empty] | 2026-04-17 00:00:00 | 2026-06-17 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF10B_PT_Schedule REM Tech installation/commission |  | TRUE | 2026-04-20 10:35:27 | chelsea@republicmetering.co.za | chelsea@republicmetering.co.za | 2026-05-18 13:05:43
REM - Work in Progress Warehouse | JC10701 | Caperfield Investments (Pty) Ltd | CS10059 |  | Melissa Russell | maintenance@mp365.co.za |  | FF_Fault Fix Water (Lora/Visio) | The meter has stopped communicating since the 16th. It is a PP meter, so we need to get it sorted asap. |  | Maitland Industrial Park 5 Mowbray Road Maitland Cape Town | 2026-04-20 11:08:35 | 32 | 17 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-05-05 10:36:38 | [7 empty] | Box Complete-20MM Plastic SA1508 SABS V (BCP20M20) [210401821] | PR-DWM-PVC-20/20mm | 210401821 |  | Donovan Willemse, Zoë Wille |  |  |  | Unit B08 | [5 empty] | 2026-04-16 00:00:00 | 2026-04-20 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-20 11:08:36 | jamie@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-05 10:36:39
REM - Work in Progress Warehouse | JC10704 | Vestspruit Suites (Pty) Ltd | CS10294 |  | Tsolofelo Makola | tmakola@trueprop.co.za | 0836265352 | FF_Fault Fix Water (Lora/Visio) | The main muni check is not recording any consumption. I suspect the lora has failed. |  | Site Manager 2 McAdams Street Mbombela | 2026-04-20 12:05:41 | 32 | 30 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-04-22 12:13:42 |  |  |  | QU3564 |  |  |  | Existing-80mm Water Meter [20704043] | Existing-80mm Water Meter | 20704043 |  | Donovan Willemse, Zoë Wille |  |  |  | Main Muni check | [5 empty] | 2026-04-20 00:00:00 | 2026-05-05 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-20 12:05:41 | jamie@republicmetering.co.za | zoe@republicmetering.co.za | 2026-04-22 12:13:42
REM - Work in Progress Warehouse | JC10705 | Nu-Sa Prop (Pty) Ltd | CS10194 |  | Sharon Fynn | sharonfynn@imaginet.co.za | 0832579955 | FF_Fault Fix Water (Lora/Visio) | The meter at Transbrikpark has not called in. |  | Sharon Fynn Cnr Zanemali Rd and Progress St Mthatha | 2026-04-21 08:17:39 | 31 | 30 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-04-22 12:25:49 |  |  |  | QU3563 |  |  |  | Existing-20mm Water Meter [232032745] | Existing-20mm Water Meter | 232032745 |  | Donovan Willemse, Zoë Wille |  |  |  | Unit 09A | [5 empty] | 2026-04-18 00:00:00 | 2026-07-17 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-21 08:17:40 | jamie@republicmetering.co.za | zoe@republicmetering.co.za | 2026-04-22 12:25:49
REM - Work in Progress Warehouse | JC10707 | Beer Properties (Pty) Ltd | CS10042 |  | Yolande Potgieter | yolande@thebeergroup.co.za | 0466362894 | FF_Fault Fix Elec meter with modem | The meter has lost communication with Scada, please resolve. |  | 77 Bridge St Mthatha | 2026-04-21 09:50:36 | 31 | 9 | FF13_LT_Update Stock Used | 2026-05-12 14:49:04 | [7 empty] | A1140 Three Phase 4W 5A 230V 0.5 TOU RS232 ESK Complex Mid-Range Meters [68108957] | LM3MAABBNHESRBFESK | 68108957 |  | Donovan Willemse, Justin Bezuidenhout |  |  |  | Bridge St - Ackermans | [5 empty] | 2026-04-16 00:00:00 | 2026-04-28 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback > FF10B_PT_Schedule REM Tech installation/commission > FF12.2_QT_Install Sign Off > FF13_LT_Update Stock Used |  | TRUE | 2026-04-21 09:50:36 | jamie@republicmetering.co.za | lindy@republicmetering.co.za | 2026-05-12 14:49:04
REM - Work in Progress Warehouse | JC10708 | The Circle (Pty) Ltd | CS10267 |  | Lize Price | LPrice@trueprop.co.za | 0609611007 | FF_Fault Fix Water (Lora/Visio) | Meter is still connected to a visio ( 028EB317 ) we need to quote on replacing with a smart meter |  | Kings Mall, Main Road, East London, 5201, (Lize Price - 0609611007) | 2026-04-21 09:53:21 | 31 | 15 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-05-07 14:45:28 |  |  |  | QU3567 |  |  |  | Existing-20mm Water Meter [C-SAG8633] | Existing-20mm Water Meter | C-SAG8633 |  | Donovan Willemse, Zoë Wille |  |  |  | Shop 36 - Glammer Zone | [5 empty] | 2026-04-13 00:00:00 | 2026-04-16 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-21 09:53:21 | jamie@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-07 14:45:28
REM - Work in Progress Warehouse | JC10710 | Vimba Trading (Pty) Ltd | CS10296 |  | Jessica Kennedy | jess@wildcoast.co.za |  | IN_Electrical Install (REM Subbie) | Good morning Chelsea, I hope you are well. Please could you forward this to the relevant person if not you. Russell's has a second tenant running off of their electrical supply - is it possible for you to install a meter to monitor that so the second tenant can pay Russell's for their consumption? Kind regards, Jess SenseCo |  | Site Manager Richardson Road Idutywa | 2026-04-21 11:38:55 | 31 | 29 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-04-23 12:39:42 |  |  |  | QU3568 | [7 empty] | Donovan Willemse, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-21 11:38:55 | lindy@republicmetering.co.za | lindy@republicmetering.co.za | 2026-04-28 08:41:57
REM - Work in Progress Warehouse | JC10711 | Autobahn Properties (Pty) Ltd | CS10040 |  | Sarah Lower | accounts3@bmiza.com |  | FF_Fault Fix Kamstrup Server Meter (Elec/Wat) | All meters connected to modem are down. ( MSC30028 ) |  | LBPQ 8 Stephenson St PE | 2026-04-22 08:12:07 | 30 | 30 | FF10B_PT_Schedule REM Tech installation/commission | 2026-04-22 10:40:18 | [7 empty] | A1140 Three Phase 4W 5A 230V 0.5 TOU RS232 ESK Complex Mid-Range Meters [88101104], A1140 Three Phase 4W 100A 230V 1.0 TOU RS232 ESK Complex Mid-Range Meters [18130576], A1140 Three Phase 4W 100A 230V 1.0 TOU RS232 ESK Complex Mid-Range Meters [18130591], A1700,3P4W ,1-6A,63-240V ,0.5,TO U,ESK [31505126] | LM3MAABBNHESRBFESK, LM3BABBBNHESRRFESK, LM3BABBBNHESRRFESK, EL-A1700 1-6A PB3FAAGPNN3KESK | 88101104, 18130576, 18130591, 31505126 |  | Donovan Willemse, Justin Bezuidenhout |  |  |  | Muni Check; Units 1 - 3 | [5 empty] | 2026-04-19 00:00:00 | 2026-05-04 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF10B_PT_Schedule REM Tech installation/commission |  | TRUE | 2026-04-22 08:12:09 | jamie@republicmetering.co.za | susan@republicmetering.co.za | 2026-05-21 09:21:36
REM - Work in Progress Warehouse | JC10713 | Moneyline 553 (Pty) Ltd | CS10183 |  | Tarryn Jenkins | tarryn@globalbusiness.co.za | 0729723591 | FF_Fault Fix Elec meter with modem | Meter connected ( MGC0981) |  | Vodacom Building 4 Stewart Drive Baysville East London | 2026-04-22 08:21:32 | 30 | 3 | FF12.1_PT_Install complete capture info | 2026-05-19 11:05:22 | [7 empty] | A1140 Three Phase 4W 5A 230V 0.5 TOU RS232 ESK Complex Mid-Range Meters [38134446] | LM3MAABBNHESRBFESK | 38134446 |  | Donovan Willemse, Justin Bezuidenhout |  |  |  | Vodacom | [5 empty] | 2026-04-19 00:00:00 | 2026-05-07 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback > FF10B_PT_Schedule REM Tech installation/commission > FF12.1_PT_Install complete capture info |  | TRUE | 2026-04-22 08:21:33 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-19 11:05:23
REM - Work in Progress Warehouse | JC10721 | Dorbyl Uitenhage (EBOR) | CS10836 |  | Brendon Naidoo | brendon@ebor.co.za | 0826026138 | IN_Electrical Install (REM Subbie) | Ebor - They want their own internal meter/s to quantify their usage and compare with the bill that they are receiving from SKG? |  | SKG - Dorbyl Uitenhage (EBOR) Dorbyl Uitenhage, Alexander Park, Kariega, 6229 | 2026-04-22 13:07:57 | 30 | 30 | SI02_PT_Inspection Scheduled | 2026-04-22 14:01:16 | [11 empty] | Donovan Willemse, Justin Bezuidenhout, Lindy Maritz | [13 empty] | FALSE | SI01_PT_Job Loaded > SI02_PT_Inspection Scheduled |  | TRUE | 2026-04-22 13:07:57 | lindy@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-14 12:12:26
REM - Work in Progress Warehouse | JC10723 | GM Industrial Park Body Corporate (SLA) | CS10109 |  | Neill Hodgskin | maintenance@bmiza.com | 0719007429 | IN_Electrical Install (Client subbie) | QRY10216 created for a stock sale as Leshay did not have more details of the job. Genergy wants 2 x CT meters that they will be installing at GM. We will then onboard the meters. 1. Building 1 - PV 400/5A, 2. Hasty Tasty PV - 500/5A. Waiting for them to issue a PO/payment will then send the stock to them in PE. Will programme the meters upfront. Siphesihle (0718202622) is the contact person. Loading a JC so long. |  | GM Industrial Park Kempston Road Gqebhera 6001 (Neill) | 2026-04-22 15:44:54 | 29 | 3 | IN11.1_PT_Awaiting install by client | 2026-05-19 12:27:10 | [11 empty] | Donovan Willemse, Joanne Kumm, Kyle de Agrella, Lindy Maritz, Projects Technical | [13 empty] | FALSE | SI01_PT_Job Loaded > IN11.1_PT_Awaiting install by client | QRY10216 | TRUE | 2026-04-22 15:44:54 | info@republicmetering.co.za | info@republicmetering.co.za | 2026-05-21 09:55:53
REM - Work in Progress Warehouse | JC10725 | Robhoek Farm | CS10840 |  | Nigel Lok | nigel@robhoek.co.za |  | IN_Electrical Install (REM Subbie) | U CAN SOLAR Site Need price to fit 2 meters , 300amp split core ct’s in Tsitsikama. 160A point requiring metering. Price on Solid Core CT’s |  | X53M+VQF Woodlands | 2026-04-23 10:39:44 | 29 | 8 | IN11.2_PT_Schedule REM Tech installation/commission | 2026-05-14 08:42:07 |  |  |  | QU3576 | [6 empty] | Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp, Ring CT 30/40mm ID 200/5A CLS 0,5, Split CT UK 40mm ID 300/5A, Small Steel Enclosure 400 x 300 x 200 IP 65, Riecktron M2M Kamstrup Plug In Modem (incl antenna), Installation & Commissioning (less than 7 Meters), Travel Cost, Quote Subject to Change, 50% Deposit required | Donovan Willemse, Kyle de Agrella, Sean Knoetze | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval > IN10_LT_ Job Approved Send Stock > IN11.2_PT_Schedule REM Tech installation/commission |  | TRUE | 2026-04-23 10:39:45 | donovan@republicmetering.co.za | kyle@republicmetering.co.za | 2026-05-19 10:58:40
REM - Work in Progress Warehouse | JC10729 | Bellingan Properties (Pty) Ltd | CS10043 |  | Aldo Bellingan | aldo@bellinganproperties.co.za | 0713824803 | IN_Electrical Install (Client subbie) | Can we please get a quote for a single phase, inline meter, for a 63amp single phase supply. This will be an additional meter for 274 cape Road. |  | 274 Kaleidoscope (Vodacom Acres) 274 Cape Road Newton Park Gqeberha | 2026-04-23 16:28:55 | 28 | 7 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-05-14 15:56:18 |  |  |  | QU3583 | [7 empty] | Donovan Willemse, Lindy Maritz, Susan Cornelius, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI04_FT_Quote Population > SI03.2_QT_Quotation Sign Off > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-23 16:28:55 | lindy@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-14 15:56:24
REM - Work in Progress Warehouse | JC10730 | Derprops 113 (Pty) Ltd | CS10082 |  | Christiaan Rust | christiaan@neulux.co.za | 0824630862 | FF_Fault Fix Elec meter with modem | Multiple meters connected to the site is down. Please resolve comms |  | Derprops Industrial Park 23 Wimbledon Road Blackhealth Cape Town | 2026-04-24 08:27:13 | 28 | 28 | FF03.1_PT_Awaiting Client Feedback | 2026-04-24 10:44:34 | [7 empty] | Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [35778903], Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [35779552], Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [35779553], Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [35779550], Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [35266734], Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [35266685], Kamstrup Omnipower V2 Three Phase CT Connect 5 Amp [35266684] | 685-11-355-D24-0111-120, 685-11-355-D24-0111-120, 685-11-355-D24-0111-120, 685-11-355-D24-0111-120, 685-11-355-D24-0111-120, 685-11-355-D24-0111-120, 685-11-355-D24-0111-120 | 35778903, 35779552, 35779553, 35779550, 35266734, 35266685, 35266684 |  | Donovan Willemse |  |  |  | Multiple | [5 empty] | 2026-04-21 00:00:00 | 2026-05-05 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback |  | TRUE | 2026-04-24 08:27:14 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-04-24 10:44:34
REM - Work in Progress Warehouse | JC10732 | Trueprop Facilities (Pty) Ltd | CS10283 |  | Amaara Khan (32 Dyer) | akhan@trueprop.co.za | 0437000160 | FF_Fault Fix Water (Lora/Visio) | Meter is still connected to a visio ( 01FBF93F ) and has now lost connectivity |  | 32 Dyer St Arcadia East London 5201 | 2026-04-24 08:44:56 | 28 | 3 | FF10A_PT_Awaiting install by client's techie | 2026-05-18 16:11:03 |  |  |  | QU3603 |  |  |  | Visios [01FBF93F], Existing-20mm Water Meter [C-VKE6098] | VIS-VISIO, Existing-20mm Water Meter | 01FBF93F, C-VKE6098 | Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus | Donovan Willemse |  |  |  | Unit 04 - Spacemakers | [5 empty] | 2026-04-21 00:00:00 | 2026-07-06 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.3_QT_Quotation Sign Off > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie |  | TRUE | 2026-04-24 08:44:57 | jamie@republicmetering.co.za | info@republicmetering.co.za | 2026-05-18 16:11:03
REM - Work in Progress Warehouse | JC10735 | Lumibiz (PTY) Ltd | CS10169 |  | Abraham Marais | abraham@fvcec.co.za | 0836318822 | FF_Fault Fix Water (Lora/Visio) | Meter has been down for 3 days - gateway is up, but the lora shows offline. Please note we do not estimate on muni checks, so we need to either resolve or quote on replacing, but take now its a big one. Scada says 150mm but in Servcraft it is 50 - not sure why this discrepancy is there |  | Abraham Marais Shop 19, Gateway Corner Sarel Baard Crescent Rooihuiskraal, Centurion | 2026-04-24 10:34:08 | 28 | 17 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-05-05 11:44:43 |  |  |  | QU3598 |  |  |  | Existing-50mm Water Meter [19725069] | Existing-50mm Water Meter | 19725069 |  | Donovan Willemse, Zoë Wille |  |  |  | Muni check | [5 empty] | 2026-04-21 00:00:00 | 2026-05-20 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.3_QT_Quotation Sign Off > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-24 10:34:10 | jamie@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-05 11:44:43
REM - Work in Progress Warehouse | JC10763 | St Giles House (Pty) Ltd | CS10247 |  | Siyabonga Holoshe (Property Manager - 3 Factory) | shololoshe@trueprop.co.za | 0716883879 | FF_Fault Fix Water (Lora/Visio) | 2145003748 not calling in. Muni Check meter, cannot be estimated. Billing due on the 4th. |  | 3 Factory Rd Queenstown Komani 5320 | 2026-04-29 08:19:21 | 23 | 14 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-05-07 14:58:42 |  |  |  | QU3602 |  |  |  | INFINITY EVO - BULK METER, CLASS C, T16 80mm [2145003748] | PR-EVO-BWM-80mm (EVODN80CT16T) | 2145003748 |  | Donovan Willemse, Zoë Wille |  |  |  | Muni Check | [5 empty] | 2026-04-24 00:00:00 | 2026-07-24 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.3_QT_Quotation Sign Off > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-04-29 08:19:22 | chelsea@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-07 14:58:42
REM - Work in Progress Warehouse | JC10765 | InoFort Proprietary Limited [Island Works] | CS10130 |  | Simphiwe Phelo | spehlo@inospace.com | 0681180671 | FF_Fault Fix Elec meter with modem | 48128064 + 48123813 connected to modem MSS57409 are not calling in. Think it could be the modem. Billing due on the 8th. 32910683 Unit 21 connected to modem MSS33364 also affected. |  | Island Works 22 Cumberland Rd Paarden Eiland Cape Town | 2026-04-29 08:36:27 | 23 | 2 | FF09.2_LT_Job Approved Send Stock | 2026-05-20 14:05:08 |  |  |  | QU3633 |  |  |  | A1140 Three Phase 4W 5A 230V 0.5 TOU RS232 ESK Complex Mid-Range Meters [48123813], A1140 Three Phase 4W 5A 230V 0.5 TOU RS232 ESK Complex Mid-Range Meters [48128064], Riecktron M2M External Modem with PSU (incl antenna) [MSS57409], Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [32910683], Riecktron M2M External Modem with PSU (incl antenna) [MSS66634] | LM3MAABBNHESRBFESK, LM3MAABBNHESRBFESK, M2M-MSS-B(RIECK), 684-11-311-N24-5111-120, M2M-MSS-B(RIECK) | 48123813, 48128064, MSS57409, 32910683, MSS66634 |  | Donovan Willemse, Lizette Benn, Tanya Redelinghuys |  |  |  | Unit 05 and Unit 23+24 + Unit 21 | [5 empty] | 2026-04-26 00:00:00 | 2026-07-08 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback > FF03.3_QT_Quotation Sign Off > FF04.1_FT_Quote population > FF03.3_QT_Quotation Sign Off > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock |  | TRUE | 2026-04-29 08:36:28 | chelsea@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-20 14:05:17
REM - Work in Progress Warehouse | JC10775 | East Cape Farms (Pty)Ltd | CS10846 |  | Garick Christiani | ecf@ecffarming.co.za | 0833210131 | IN_Electrical Install (REM Subbie) | U CAN SOLAR Site Ant requested that we quote this client for 2x check meters. 2x 150A supplies. |  | Xuka Drift M2HC+WQ7 Dulwane Ugie Area | 2026-05-04 08:49:24 | 18 | 17 | SI07_FT_Quote Sent Awaiting Customer Approval | 2026-05-05 11:19:29 |  |  |  | QU3597 | [7 empty] | Donovan Willemse, Lindy Maritz, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > SI03.2_QT_Quotation Sign Off > SI04_FT_Quote Population > SI05_FT_Quote Review > SI06_FT_Quote Amend/Send > SI07_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-05-04 08:49:24 | donovan@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-05 11:19:29
REM - Work in Progress Warehouse | JC10779 | Wild Oke (Pty) Ltd | CS10301 |  | Rolene | rentals@remaxfrontier.co.za |  | FF_Fault Fix Water (Lora/Visio) | The meter has not been calling in for a while. We had an open JC on Centricity, we probably didnt reopen with the crossover. |  | Antony Wannell 1 Croft Street West Hill Makhanda | 2026-05-04 11:58:29 | 18 | 1 | FF06_FT_Quote Sent Awaiting Customer Approval | 2026-05-21 09:57:51 |  |  |  | QU10011, QU3599 |  |  |  | Existing-Unknown Water Meter [230037725] | Existing-Unknown Water Meter | 230037725 |  | Donovan Willemse, Lindy Maritz, Zoë Wille |  |  |  | House and Flat | [5 empty] | 2025-09-19 00:00:00 | 2026-05-04 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.3_QT_Quotation Sign Off > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval |  | TRUE | 2026-05-04 11:58:29 | jamie@republicmetering.co.za | zoe@republicmetering.co.za | 2026-05-21 09:57:51
REM - Work in Progress Warehouse | JC10781 | Styleprops 163 (Pty) Ltd | CS10253 |  | Wendy Stander | wendy@wgproperties.co.za | 0833949719 | FF_Fault Fix Water (Lora/Visio) | The meter is still connected to a visio (00C652C7) The screen is completely black so our assumption is the visio is dead. Billing due on the 14th |  | Gonubie Centre Unknown (Wendy) | 2026-05-04 14:52:39 | 17 | 8 | FF10A_PT_Awaiting install by client's techie | 2026-05-14 11:58:28 |  |  |  | QU3610 |  |  |  | Visios [00C652C7], Existing-15mm Water Meter [C-VAB3321], Existing-25mm Water Meter [C-VJK6249], Visios [028EB78F], Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 [54043183], Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 [54043184] | VIS-VISIO, Existing-15mm Water Meter, Existing-25mm Water Meter, VIS-VISIO, 02K-51-AC6G-8ZA, 02K-51-AC6G-8ZA | 00C652C7, C-VAB3321, C-VJK6249, 028EB78F, 54043183, 54043184 | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 | Donovan Willemse, Zoë Wille |  |  |  | Flat 03+Flat 11 | [5 empty] | 2026-04-28 00:00:00 | 2026-07-14 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.3_QT_Quotation Sign Off > FF04.1_FT_Quote population > FF04.2_FT_Quote to Approve Internal > FF05_FT_Quote Amend/Send > FF06_FT_Quote Sent Awaiting Customer Approval > FF09.2_LT_Job Approved Send Stock > FF10A_PT_Awaiting install by client's techie |  | TRUE | 2026-05-04 14:52:39 | jamie@republicmetering.co.za | info@republicmetering.co.za | 2026-05-14 11:58:28
REM - Work in Progress Warehouse | JC10797 | Inofort Proprietary Limited [Wynberg Workshops Block C] | CS10305 |  | Nadine Beyleveld | nbeyleveld@inospace.com |  | FF_Fault Fix Kamstrup Server Meter (Elec/Wat) | Meter for C07 is not calling in. |  | Wynberg Workshops Block C 43 5th Street, Wynberg, Sandton, Johannesburg, 2090 (Nadine) | 2026-05-07 08:24:14 | 15 | 0 | FF03.1_PT_Awaiting Client Feedback | 2026-05-22 10:25:53 | [7 empty] | Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [34977892] | 684-11-311-N24-5111-120 | 34977892 |  | Donovan Willemse |  |  |  | Unit C07 - (Prepaid) | [5 empty] | 2026-05-04 00:00:00 | 2026-05-11 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF02.2_PT_Further Investigations > FF03.1_PT_Awaiting Client Feedback |  | TRUE | 2026-05-07 08:24:17 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-22 10:25:53
REM - Work in Progress Warehouse | JC10799 | Inospace 5 Proprietary Limited [Allandale Exchange] | CS10143 |  | Charne Du Plessis | charned@inospace.com | 0847727963 | FF_Fault Fix Kamstrup Server Meter (Elec/Wat) | Meter has stopped communicating with us. |  | Allandale Exchange 917 Morkel's Place Halfway House Midrand | 2026-05-07 08:27:54 | 15 | 0 | FF03.1_PT_Awaiting Client Feedback | 2026-05-22 10:25:27 | [7 empty] | Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [35267518] | 684-11-311-N24-5111-120 | 35267518 |  | Donovan Willemse |  |  |  | Common Areas mini sub | [5 empty] | 2026-05-04 00:00:00 | 2026-05-11 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF02.2_PT_Further Investigations > FF03.1_PT_Awaiting Client Feedback |  | TRUE | 2026-05-07 08:27:57 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-22 10:25:27
REM - Work in Progress Warehouse | JC10803 | Mabovula Butchery KWY (Pty) Ltd | CS10170 |  | Butchery KWY (Pty) Ltd | mabovulakwt@gmail.com |  | IN_Electrical Install (REM Subbie) | Justin to commission the existing kamstrup meter measuring the PV. We will invoice Gareth afterwards for the modem and commissioning. As requested by Gareth Mack |  | Mabovula Butchery 20 Wellington Street King Williams Town | 2026-05-07 11:29:14 | 15 | 3 | IN13.1_PT_Install complete capture info | 2026-05-19 08:24:48 | [11 empty] | Donovan Willemse, Justin Bezuidenhout | [13 empty] | FALSE | SI01_PT_Job Loaded > IN11.2_PT_Schedule REM Tech installation/commission > IN13.1_PT_Install complete capture info |  | TRUE | 2026-05-07 11:29:14 | donovan@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-19 08:24:49
REM - Work in Progress Warehouse | JC10807 | InoFort (Pty) Ltd [Textile Exchange] | CS10126 |  | Liam Vickers | lvickers@inospace.com |  | FF_Fault Fix Kamstrup Server Meter (Elec/Wat) | 76609164 not calling in. Billing due on the 8th. |  | Textile Exchange 19 Textiel Street Parow Industria Cape Town | 2026-05-07 15:48:03 | 14 | 11 | FF03.1_PT_Awaiting Client Feedback | 2026-05-11 09:18:59 | [7 empty] | Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [76609164] | 021-40-C04-894 | 76609164 |  | Donovan Willemse |  |  |  | Unit 4 | [5 empty] | 2026-04-15 00:00:00 | 2026-08-08 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback |  | TRUE | 2026-05-07 15:48:03 | chelsea@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-11 09:18:59
REM - Work in Progress Warehouse | JC10808 | Vestspruit Suites (Pty) Ltd | CS10294 |  | Deon Bekker | dbecker@trueprop.co.za |  | FF_Fault Fix Elec meter with modem | Multiple meters connected to the modem ( M31813) is down. |  | 12 Middle Rd, Anderbolt, Boksburg, 1459 | 2026-05-08 09:45:24 | 14 | 14 | FF10B_PT_Schedule REM Tech installation/commission | 2026-05-08 10:19:35 | [7 empty] | Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [32911977], Existing Electrical Meter [36929508], Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [33493730], Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [36084626], Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [33493724], Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [33493729] | 684-11-311-N24-5111-120, Existing Electrical Meter, 684-11-311-N24-5111-120, 684-11-311-N24-5111-120, 684-11-311-N24-5111-120, 684-11-311-N24-5111-120 | 32911977, 36929508, 33493730, 36084626, 33493724, 33493729 |  | Donovan Willemse, James Nicholls |  |  |  | Multiple | [5 empty] | 2026-05-05 00:00:00 | 2026-05-29 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF10B_PT_Schedule REM Tech installation/commission |  | TRUE | 2026-05-08 09:45:26 | jamie@republicmetering.co.za | info@republicmetering.co.za | 2026-05-21 12:23:57
REM - Work in Progress Warehouse | JC10814 | Inrabiz Proprietary Limited [Sebenza Works] | CS10146 |  | Sharon da Silva | sdasilva@inospace.com | 0876250490 | FF_Fault Fix Elec meter with modem | The meter has a note that the load cable has been removed, but it is no longer vacant. So there is no consumption. |  | Sebenza Works, 131 Terrace Road, Sebenza Edenvale, Johannesburg, 1609 (Chane and Leander) | 2026-05-11 10:37:13 | 11 | 10 | FF03.1_PT_Awaiting Client Feedback | 2026-05-11 16:25:48 | [7 empty] | Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [33493414] | 684-11-311-N24-5111-120 | 33493414 |  | Donovan Willemse |  |  |  | Unit 11 - Nova Power | [5 empty] | 2025-09-24 00:00:00 | 2026-05-11 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback |  | TRUE | 2026-05-11 10:37:14 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-11 16:25:48
REM - Work in Progress Warehouse | JC10816 | Midgallagher Industrial Park (Pty) Ltd | CS10178 |  | Innocent Nkondlwane | innocentn2@servest.co.za | 0820711063 | FF_Fault Fix Water Kamstrup with Gateway | A few meters have been down since Friday, we need to resolve comms. And these are not meters that call in sporadically. |  | Site Manager 33 Orchards Drive Richards Rd Halfway House | 2026-05-12 09:26:39 | 10 | 9 | FF03.1_PT_Awaiting Client Feedback | 2026-05-13 08:56:01 | [7 empty] | Kamstrup DN15 (20mm) FlowIQ2200 Composite Threaded 110mm cold water 1.5kl/h R250 WM-Bus/LinkIQ [12992737], Kamstrup DN15 (20mm) FlowIQ2200 Composite Threaded 110mm cold water 1.5kl/h R250 WM-Bus/LinkIQ [12992739], Kamstrup DN15 (20mm) FlowIQ2200 Composite Threaded 110mm cold water 1.5kl/h R250 WM-Bus/LinkIQ [12992741], Kamstrup DN15 (20mm) FlowIQ2200 Composite Threaded 110mm cold water 1.5kl/h R250 WM-Bus/LinkIQ [12992740] | 02K-51-AC1B-817, 02K-51-AC1B-817, 02K-51-AC1B-817, 02K-51-AC1B-817 | 12992737, 12992739, 12992741, 12992740 |  | Donovan Willemse |  |  |  | Units 01, 02, 03, 04 | [5 empty] | 2026-05-08 00:00:00 | 2026-05-13 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback |  | TRUE | 2026-05-12 09:26:40 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-13 08:56:02
REM - Work in Progress Warehouse | JC10820 | Eagle Creek Investments 319 (Pty) Ltd | CS10088 |  | Abraham Marais | abraham@fvcec.co.za |  | FF_Fault Fix Water Kamstrup with Gateway | Meter is not communicating with us. Please can we resolve comms. Billing due 19th. |  | Old Showgrounds Martin St Sydenham Gqebhera | 2026-05-13 09:27:48 | 9 | 0 | FF13_LT_Update Stock Used | 2026-05-22 14:35:26 | [7 empty] | Kamstrup DN100 FlowIQ3200 Stainless Steel Flanged 360mm cold water 60kl/h R250 WM-Bus/LinkIQ [54257996] | 02L-60-DCAJ-8ZA | 54257996 |  | Donovan Willemse, Justin Bezuidenhout |  |  |  | Unit 1 - Fresenius Kabi | [5 empty] | 2026-05-09 00:00:00 | 2026-05-20 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF02.2_PT_Further Investigations > FF12.2_QT_Install Sign Off > FF13_LT_Update Stock Used |  | TRUE | 2026-05-13 09:27:49 | jamie@republicmetering.co.za | lindy@republicmetering.co.za | 2026-05-22 14:35:26
REM - Work in Progress Warehouse | JC10825 | U CAN SOLAR (Pty) Ltd | CS10769 |  | Anthony Schwedhelm | Ant@u-cansolar.co.za |  | IN_Electrical Install (REM Subbie) | Data importing. |  | 3 Kloof Street Gonubie North East London Eastern Cape | 2026-05-14 14:08:43 | 8 | 7 | IN18_FT_Final invoice and check monthlies | 2026-05-15 10:39:46 | [11 empty] | Donovan Willemse, Zoë Wille | [13 empty] | FALSE | SI01_PT_Job Loaded > IN15_BT_Billing Scada Setup > IN18_FT_Final invoice and check monthlies |  | TRUE | 2026-05-14 14:08:44 | donovan@republicmetering.co.za | zelda@republicmetering.co.za | 2026-05-15 10:39:46
REM - Work in Progress Warehouse | JC10826 | Value Logistics (Pty) Ltd | CS10289 |  | Eugene Blanche | eugeneb@wonderlandprop.co.za |  | FF_Fault Fix Elec meter with modem | Meter has not connected to us. It is connected to the modem ( MSS29997 ) |  | Site Manager 10 Essex St Tunney Ext. 10 Germiston | 2026-05-15 08:39:31 | 7 | 0 | FF09.2_LT_Job Approved Send Stock | 2026-05-22 12:51:27 | [7 empty] | A1140 Three Phase 4W 5A 230V 0.5 TOU RS232 ESK Complex Mid-Range Meters [68116776], A1140 Three Phase 4W 5A 230V 0.5 TOU RS232 ESK Complex Mid-Range Meters [68116769] | LM3MAABBNHESRBFESK, LM3MAABBNHESRBFESK | 68116776, 68116769 |  | Donovan Willemse, Lizette Benn |  |  |  | DB MSS 1 & MSS 2 | [5 empty] | 2026-05-13 00:00:00 | 2026-06-15 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF10B_PT_Schedule REM Tech installation/commission > FF03.3_QT_Quotation Sign Off > FF04.1_FT_Quote population > FF09.2_LT_Job Approved Send Stock |  | TRUE | 2026-05-15 08:39:32 | jamie@republicmetering.co.za | lindy@republicmetering.co.za | 2026-05-22 14:22:17
REM - Work in Progress Warehouse | JC10830 | Energyworx | CS10095 |  | Khaled El-Jabi | khaled@energyworxsa.com | 0734541412 | IN_Electrical Install (Client subbie) | Please can you get the info of what these three meters measure? We need to update scada and then pass on to billing to upload. 35779523 - EDEN VIEW 35779525 - EDEN VIEW 35779536 - EDEN VIEW |  | Eden View Lifestyle Estate N2, Plettenberg Bay, 6600 (Khaled) | 2026-05-15 15:16:27 | 6 | 6 | IN13.1_PT_Install complete capture info | 2026-05-15 15:16:57 | [11 empty] | Donovan Willemse, Kyle de Agrella | [13 empty] | FALSE | SI01_PT_Job Loaded > IN13.1_PT_Install complete capture info |  | TRUE | 2026-05-15 15:16:28 | susan@republicmetering.co.za | susan@republicmetering.co.za | 2026-05-15 15:16:57
REM - Work in Progress Warehouse | JC10837 | Donvin Properties (Pty) Ltd | CS10087 |  | Tracey-Lee Endley | tendley@trueprop.co.za | 0765221269 | FF_Fault Fix Water Kamstrup with Gateway | The new KMP water meter has not called in, we need to resolve comms please. |  | Fish Hoek 1st Floor Town Square Main Rd Fish Hoek | 2026-05-19 09:54:50 | 3 | 0 | FF04.1_FT_Quote population | 2026-05-22 14:19:24 | [7 empty] | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 [54043871] | 02K-51-AC6G-8ZA | 54043871 |  | Donovan Willemse, Zoë Wille |  |  |  | Woolworths Food | [5 empty] | 2026-05-15 00:00:00 | 2026-06-05 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF02.2_PT_Further Investigations > FF03.3_QT_Quotation Sign Off > FF04.1_FT_Quote population |  | TRUE | 2026-05-19 09:54:50 | jamie@republicmetering.co.za | lindy@republicmetering.co.za | 2026-05-22 14:19:32
REM - Work in Progress Warehouse | JC10846 | Clublink (Pty) Ltd | CS10069 |  | Yolande Potgieter | Yolande@thebeergroup.co.za | 0466362894 | FF_Fault Fix Kamstrup Server Meter (Elec/Wat) | Meter in the kiosk is not calling in. |  | PGM (Peppergrove Mall) African Street Grahamstown 6139 | 2026-05-21 08:36:22 | 1 | 1 | FF02.1_PT_Troubleshoot Remotely | 2026-05-21 08:36:34 | [7 empty] | Kamstrup Omnipower V2 Three Phase Direct Connect 100 Amp [36114389] | 684-11-311-N24-5111-120 | 36114389 |  | Donovan Willemse |  |  |  | PGM - Tekkie Town Kiosk 2 - Shop 27 | [5 empty] | 2026-05-18 00:00:00 | 2026-05-28 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely |  | TRUE | 2026-05-21 08:36:23 | jamie@republicmetering.co.za | jamie@republicmetering.co.za | 2026-05-21 08:36:34
REM - Work in Progress Warehouse | JC10847 | Donvin Properties (Pty) Ltd | CS10087 |  | Tracey-Lee Endley | tendley@trueprop.co.za | 0765221269 | FF_Fault Fix Water Kamstrup with Gateway | Some meters that have not called in, I checked on M2M and there is not consumption since the 15th |  | Fish Hoek 1st Floor Town Square Main Rd Fish Hoek | 2026-05-21 08:52:18 | 1 | 1 | FF02.1_PT_Troubleshoot Remotely | 2026-05-21 08:52:27 | [7 empty] | Kamstrup FlowIQ2200 Qp2,5m3/h,G1B(R¾)X130MM DN20,pN16 [54043871] | 02K-51-AC6G-8ZA | 54043871 |  | Donovan Willemse, Joanne Kumm |  |  |  | Fish Hoek - Shop 05 to 07 - Woolworths (Hot Food) | [5 empty] | 2026-05-15 00:00:00 | 2026-06-05 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely |  | TRUE | 2026-05-21 08:52:19 | jamie@republicmetering.co.za | jamie@republicmetering.co.za | 2026-05-21 08:52:28
REM - Work in Progress Warehouse | JC10848 | Seven Seasons 214 (Pty) Ltd | CS10234 |  | Sharon Fynn | sharonfynn@imaginet.co.za | 2712345678 | FF_Fault Fix Water Kamstrup with Gateway | Meter has not connected in a few days. Need to resolve comms issues |  | Site Manager Unknown | 2026-05-21 08:58:07 | 1 | 1 | FF02.1_PT_Troubleshoot Remotely | 2026-05-21 08:58:18 | [7 empty] | Kamstrup DN15 (20mm) FlowIQ2200 Composite Threaded 110mm cold water 1.5kl/h R250 WM-Bus/LinkIQ [12992775] | 02K-51-AC1B-817 | 12992775 |  | Donovan Willemse |  |  |  | Hillcrest - Shop 01 - Spar Tops - Water | [5 empty] | 2026-05-18 00:00:00 | 2026-06-15 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely |  | TRUE | 2026-05-21 08:58:08 | jamie@republicmetering.co.za | jamie@republicmetering.co.za | 2026-05-21 08:58:18
REM - Work in Progress Warehouse | JC10852 | Inospace 2 (Pty) Ltd - Silo Exchange | CS10666 |  | Clinton Theys | ctheys@inospace.com |  | FF_Fault Fix Elec meter with modem | The meter connected to the modem ( MSS6384) is not calling in |  | Silo Exchange Brug St, Triangle Farm, Cape Town, 7530 | 2026-05-22 08:13:25 | 0 | 0 | FF03.1_PT_Awaiting Client Feedback | 2026-05-22 12:31:38 | [7 empty] | AS3000 Three Phase SMART Meter (AS3000) [6552365] | EL-AS3000 | 6552365 |  | Donovan Willemse |  |  |  | Unit 14 - FG Generators | [5 empty] | 2026-05-17 00:00:00 | 2026-05-29 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback |  | TRUE | 2026-05-22 08:13:26 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-22 12:31:38
REM - Work in Progress Warehouse | JC10853 | Caperfield Investments (Pty) Ltd | CS10059 |  | Melissa Russell | maintenance@mp365.co.za |  | FF_Fault Fix Water Kamstrup with Gateway | The KMP water meter is not connecting, please can we solve comms. |  | Maitland Industrial Park 5 Mowbray Road Maitland Cape Town | 2026-05-22 08:52:17 | 0 | 0 | FF03.1_PT_Awaiting Client Feedback | 2026-05-22 10:04:49 | [7 empty] | Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [59783576], Kamstrup DN15 (20mm) FlowIQ2200 Composite Threaded 110mm cold water 1.5kl/h R250 WM-Bus/LinkIQ [12992729], Kamstrup DN15 (20mm) FlowIQ2200 Composite Threaded 110mm cold water 1.5kl/h R250 WM-Bus/LinkIQ [12992773] | 021-40-C04-894, 02K-51-AC1B-817, 02K-51-AC1B-817 | 59783576, 12992729, 12992773 |  | Donovan Willemse |  |  |  | Unit A08 - Voltex | [5 empty] | 2026-05-19 00:00:00 | 2026-05-25 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF03.1_PT_Awaiting Client Feedback |  | TRUE | 2026-05-22 08:52:17 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-22 10:04:49
REM - Work in Progress Warehouse | JC10854 | Clublink (Pty) Ltd | CS10069 |  | Yolande Potgieter | Yolande@thebeergroup.co.za | 0466362894 | FF_Fault Fix Kamstrup Server Meter (Elec/Wat) | Meter has not called in. Please can we resolve comms. |  | PGM (Peppergrove Mall) African Street Grahamstown 6139 | 2026-05-22 08:58:03 | 0 | 0 | FF02.2_PT_Further Investigations | 2026-05-22 12:39:29 | [7 empty] | Kamstrup DN20 Multical21 Composite 130mm cold water 2.5kl/h WM-Bus [24722137] | 021-40-C04-894 | 24722137 |  | Donovan Willemse |  |  |  | Shop 03 - Washalot | [5 empty] | 2026-05-20 00:00:00 | 2026-05-28 00:00:00 |  |  | FALSE | FF01_BT_Fault picked up > FF02.1_PT_Troubleshoot Remotely > FF02.2_PT_Further Investigations |  | TRUE | 2026-05-22 08:58:04 | jamie@republicmetering.co.za | donovan@republicmetering.co.za | 2026-05-22 12:39:29
REM - Work in Progress Warehouse | JC10855 | Inospace 3 Proprietary Limited [Eastleigh Exchange] | CS10141 |  | Leander Grobbelaar | lgrobbelaar@inospace.com |  | IN_Electrical Install (REM Subbie) | Leander would like to get James to install 2x 3P meters for units 13 & 6C at Eastleigh exchange. Can you please create a JC for this? He has not been able to get me the breaker sizes for this yet. I was hoping he would get it to me before James goes to do the CT correction next week. They need to be quoted for the 2x meters plus labour. Unit 13 is being split and the old unit 13 meter should be labelled unit 9. |  | Eastleigh Exchange 37 Main Road, Eastleigh, Edenvale, 1609 (Leander) | 2026-05-22 09:22:14 | 0 | 0 | SI01_PT_Job Loaded | 2026-05-22 09:22:15 | [11 empty] | Donovan Willemse, Kyle de Agrella, Lindy Maritz | [13 empty] | FALSE | SI01_PT_Job Loaded |  | TRUE | 2026-05-22 09:22:15 | lindy@republicmetering.co.za | lindy@republicmetering.co.za | 2026-05-22 09:22:15